## Contents
Supplementary Data
From reference-class cost priors to investment choices: a back-tested screening workflow for lithium and copper projects
J. Caers — Mineral Economics (supplementary material)
Tab | Contents
Lithium cohort | 10 greenfield lithium projects (2010–2019): sanction CapEx, realized ratio, outcome (Table 1)
Copper cohort | 11 Chilean copper projects (2008–2019): sanction CapEx, realized ratio, outcome, confidence (Table 2)
Reference-class results | Per-project frozen reference-class band, inside-view band, realized ratio, PIT, coverage flags (Figure 5)
PIT calibration | Probability-integral-transform summary: KS p-values and means, pooled and by commodity (Figure 6)
Copper decision audit | Ex-ante RAV, engine choice, reconstructed realized NPV per copper project (Figure 7, Table 4/7)
Era register - lithium | Reference price and demand-growth outlook per sanction vintage (Table A2)
Era register - copper | Reference price and market outlook per sanction vintage (Table A3)
AACE dispersion | AACE estimate class to log-sigma mapping (Table A1)
Policy-event register | 41 resource-nationalism events, 2007–2026: lever, regime, instrument, primary source
Driver attribution | Sobol top driver vs realized decisive factor, per lithium project (Table 5)
Robustness | Discount x risk-aversion grid, decision-loss grids, and the shared-instrument sensitivity check
All values derive from public disclosures (NI 43-101/ASX/SEC filings, USGS, ICSG, Cochilco, IMF, V-Dem, OECD) and the paper's engine outputs.
Machine-readable equivalents (JSON) and a field-level data dictionary are in the accompanying code repository (data/).

## Lithium cohort
Lithium cohort
Source: manuscript Table 1 (cohort_tables.json). CapEx as disclosed; ratio = realized ÷ sanctioned capital.
Project | FID | Sanction CapEx | Realized ratio | Outcome
Olaroz S1 (Orocobre) | 2012 | US$229M | x1.75 | producing; profitable in boom
Mt Cattlin (Galaxy) | 2010 | US$70M | x1.30 | shut 2013 on price; restart 2016
Mt Marion (Neometals/Ganfeng) | 2015 | US$90M | x1.15 | producing through boom
Pilgangoora (Pilbara) | 2017 | US$180M | x1.17 | survived trough; boom winner
Altura Pilgangoora | 2017 | US$110M | x1.30 | receivership 2020; equity wiped
AMG Mibra (Brazil) | 2017 | US$60M | x1.05 | on budget; steady
Nemaska Whabouchi | 2018 | US$880M | x1.45 | C$375M shortfall; CCAA, zero production
Bald Hill (Tawana/Alita) | 2018 | US$42M | x1.25 | administration 2019 on price
Wodgina concentrator (MinRes) | 2018 | US$420M | x1.10 | mothballed 2019; JV sale monetized
Cauchari-Olaroz (LAC/Ganfeng) | 2019 | US$565M | x1.73 | producing 2023 into price collapse
FID = final investment decision year. Ratio 'x1.75' = realized capital 1.75× the sanction estimate.

## Copper cohort
Copper cohort
Source: manuscript Table 2 (cohort_tables.json). CapEx as disclosed; ratio = realized ÷ sanctioned capital.
Project | FID | Sanction CapEx | Realized ratio | Outcome | Conf
Caserones (JX/Mitsui) | 2010 | US$2.0B | x2.10 | chronic ramp; control sold 2023 | high
Ministro Hales (Codelco) | 2010 | ~US$2.3B | x1.30 | roaster ramp issues | med
Sierra Gorda (KGHM/Sumitomo) | 2011 | US$2.9B | x1.40 | below design; writedowns; exit 2022 | high
El Teniente NML (Codelco) | 2011 | ~US$3.3B | x1.60 | 2015 suspension; restructured | low
Escondida OGP1 (BHP) | 2012 | ~US$3.8B | x1.10 | delivered | low
Chuquicamata UG (Codelco) | 2012 | ~US$4.2B | x1.31 | slow underground ramp | med
Antucoya (AMSA/Marubeni) | 2012 | ~US$1.7B | x1.12 | suspended for review; completed | med
Encuentro Oxides (AMSA) | 2015 | US$0.64B | x1.01 | on time, on budget | med
Spence Growth Option (BHP) | 2017 | US$2.46B | x1.02 | near budget; COVID slip | med
Quebrada Blanca 2 (Teck/Sumitomo) | 2018 | US$5.2B | x1.67 | ~US$8.7B final; ramp problems | high
Rajo Inca (Codelco Salvador) | 2019 | ~US$1.3B | x1.38 | producing 2023-24 after delays | low
FID = final investment decision year. Ratio 'x1.75' = realized capital 1.75× the sanction estimate. Conf = curation confidence tier (high/med/low).

## Reference-class results
Reference-class results (per project)
Source: rf_data.json 'forest'. Bands are the frozen 80% intervals in ratio units (realized ÷ sanctioned). 'In RC band' / 'In inside band' are coverage flags. PIT = probability-integral transform under the frozen posterior.
Project | Commodity | Sanction yr | Realized ratio | RC band P10 | RC band P90 | Inside P10 | Inside P90 | PIT | In RC band | In inside band | Conf
Olaroz | Li | 2012 | 1.75 | 0.874 | 1.973 | 0.735 | 1.36 | 0.817 | TRUE | FALSE
MtCattlin | Li | 2010 | 1.3 | 0.874 | 1.973 | 0.735 | 1.36 | 0.488 | TRUE | TRUE
MtMarion | Li | 2015 | 1.15 | 0.892 | 1.919 | 0.735 | 1.36 | 0.333 | TRUE | TRUE
Pilgangoora | Li | 2017 | 1.17 | 0.911 | 1.969 | 0.735 | 1.36 | 0.326 | TRUE | TRUE
Altura | Li | 2017 | 1.3 | 0.911 | 1.969 | 0.735 | 1.36 | 0.46 | TRUE | TRUE
Nemaska | Li | 2018 | 1.45 | 0.884 | 1.931 | 0.735 | 1.36 | 0.634 | TRUE | FALSE
BaldHill | Li | 2018 | 1.25 | 0.884 | 1.931 | 0.735 | 1.36 | 0.442 | TRUE | TRUE
Wodgina | Li | 2018 | 1.1 | 0.884 | 1.931 | 0.735 | 1.36 | 0.286 | TRUE | TRUE
Cauchari | Li | 2019 | 1.73 | 0.884 | 1.931 | 0.735 | 1.36 | 0.821 | TRUE | FALSE
Mibra | Li | 2017 | 1.05 | 0.911 | 1.969 | 0.735 | 1.36 | 0.209 | TRUE | TRUE
Caserones | Cu | 2010 | 2.1 | 0.874 | 1.445 | 0.735 | 1.36 | 0.999 | FALSE | FALSE | high
Ministro Hales | Cu | 2010 | 1.3 | 0.874 | 1.445 | 0.735 | 1.36 | 0.771 | TRUE | TRUE | med
Sierra Gorda | Cu | 2011 | 1.4 | 0.874 | 1.445 | 0.735 | 1.36 | 0.868 | TRUE | FALSE | high
Escondida OGP1 | Cu | 2012 | 1.1 | 0.874 | 1.445 | 0.735 | 1.36 | 0.456 | TRUE | TRUE | low
Chuquicamata UG | Cu | 2012 | 1.31 | 0.874 | 1.445 | 0.735 | 1.36 | 0.782 | TRUE | TRUE | med
Antucoya | Cu | 2012 | 1.12 | 0.874 | 1.445 | 0.735 | 1.36 | 0.493 | TRUE | TRUE | med
El Teniente NML | Cu | 2011 | 1.6 | 0.874 | 1.445 | 0.735 | 1.36 | 0.964 | FALSE | FALSE | low
Encuentro Oxides | Cu | 2015 | 1.01 | 0.874 | 1.445 | 0.735 | 1.36 | 0.293 | TRUE | TRUE | med
Spence Growth Option | Cu | 2017 | 1.02 | 0.808 | 1.746 | 0.735 | 1.36 | 0.306 | TRUE | TRUE | med
Quebrada Blanca 2 | Cu | 2018 | 1.67 | 0.808 | 1.746 | 0.735 | 1.36 | 0.872 | TRUE | FALSE | high
Rajo Inca | Cu | 2019 | 1.38 | 0.795 | 1.721 | 0.735 | 1.36 | 0.708 | TRUE | FALSE | low
Coverage (derived):
Realized inside RC band | 19 | of 21
Realized inside inside-view band | 13 | of 21
Coverage counts are Excel formulas over the flag columns; they reproduce the manuscript's 19/21 reference-class vs 13/21 inside-view coverage.

## PIT calibration
Calibration — probability integral transform
Source: rf_data.json 'pit'. A calibrated forecaster yields PIT values indistinguishable from uniform (high KS p-value).
Set | KS p-value | Mean PIT | n
Pooled (all) | 0.155 | 0.587 | 21
Lithium | 0.684 | 0.482 | 10
Copper | 0.114 | 0.683 | 11
KS = Kolmogorov–Smirnov test against uniform. A mean near 0.5 and a non-significant p-value indicate calibration.

## Copper decision audit
Copper decision audit
Source: rf_data.json 'copper_choices'. RAV and realized NPV in US$ millions, 8% discount. Choice is the engine's enter/stage/walk verdict on frozen sanction-date information.
Project | Sanction yr | Ex-ante RAV (US$M) | Engine choice | Realized NPV (US$M) | Ratio | Conf
Caserones (JX/Mitsui) | 2010 | -1870 | walk | -2562 | 2.1 | high
Ministro Hales (Codelco) | 2010 | 30 | enter | 732 | 1.3 | med
Sierra Gorda (KGHM/Sumitomo) | 2011 | -1797 | walk | -1376 | 1.4 | high
Escondida OGP1 (BHP) | 2012 | -481 | stage | 659 | 1.1 | low
Chuquicamata UG (Codelco) | 2012 | -679 | stage | -448 | 1.31 | med
Antucoya (AMSA/Marubeni) | 2012 | -853 | walk | -433 | 1.12 | med
El Teniente NML (Codelco) | 2011 | -1368 | walk | -2599 | 1.6 | low
Encuentro Oxides (AMSA) | 2015 | -612 | walk | 588 | 1.01 | med
Spence Growth Option (BHP) | 2017 | -1545 | walk | 1776 | 1.02 | med
Quebrada Blanca 2 (Teck/Sumitomo) | 2018 | -3791 | walk | -2809 | 1.67 | high
Rajo Inca (Codelco Salvador) | 2019 | -1425 | walk | -527 | 1.38 | low
Spearman ρ (RAV vs realized, 8%): |  | 0.664
p-value: |  | 0.026
Sumitomo entered Sierra Gorda and Quebrada Blanca 2 (engine: walk); both realized negative NPV after by-product credits.

## Era register - lithium
Table A2
Source: manuscript A2 (appendix_tables.json).
Sanction year | Reference Li₂CO₃ (US$/t) | Central demand-growth outlook | Primary source
2009–2010 | ≈ 6,160 (deck) | ≈ 6.3%/yr total; Li-ion ≈ 13%/yr | USGS MYB-2010; Orocobre DFS 2011 (Roskill)
2012 | ≈ 6,750 | ≈ 11%/yr, 2012–2017 | USGS MYB-2012 (Roskill)
2015 | ≈ 6,500 | 9.5–14%/yr, 2015–2020 | USGS MYB-2015
2017 | ≈ 7,400 | ≈ 14%/yr | USGS MCS-2017
2018 | ≈ 14,000 | EV-led; first oversupply warnings | USGS MCS-2018; IEA GEO 2018
2019 | ≈ 9,500 | forecasts cut; oversupply realized | USGS MCS-2019/2020
Table A2. Era parameter register, lithium cohort (summary). Reference price and central demand outlook per sanction vintage; the full register with scenario weights and dated sources ships as supplementary material.

## Era register - copper
Table A3
Source: manuscript A3 (appendix_tables.json).
Sanction year | Reference LME copper (US$/t) | Market-balance / demand outlook | Primary source
2008 | ≈ 6,956 | China-led growth; modest surplus | USGS MCS-2008; ICSG
2010 | ≈ 7,533 | post-crisis rebound; small surplus | USGS MCS-2010; ICSG
2011 | ≈ 8,814 | supercycle peak; deficit narrative | USGS MCS-2011; ICSG
2012 | ≈ 7,950 | third consecutive deficit; turn expected | USGS MCS-2012/2013; ICSG
2015 | ≈ 5,501 | bear turn; 2015 surplus expected | USGS MCS-2015; ICSG
2017 | ≈ 6,162 | +1.0% consumption; ≈ 160 kt surplus | USGS MCS-2017; ICSG
2018 | ≈ 6,525 | near balance; electrification emerging | USGS MCS-2018; ICSG
2019 | ≈ 6,005 | electrification demand narrative | USGS MYB-2019; ICSG
Table A3. Era parameter register, copper cohort (summary). Reference price is the USGS annual-average LME level at the sanction date; balance calls are the then-current ICSG view, preserved as published.

## AACE dispersion
Table A1
Source: manuscript A1 (appendix_tables.json).
AACE class | Estimate maturity | AACE 47R-11 band (P10 / P90) | s_1 (log-σ) used
5 | scoping / order-of-magnitude | −50% / +100% | 0.45
4 | study / concept | −30% / +50% | 0.34
3 | feasibility | −20% / +30% | 0.24
2 | budget / control | −15% / +20% | 0.15
1 | tender-ready | −10% / +15% | 0.09
Table A1. Cost-engine class-to-σ mapping. s_1 is the inside-view log-dispersion assigned to each AACE estimate class, calibrated within the RP 47R-11 mining accuracy ranges (which are stated at an 80 percent confidence interval).

## Policy-event register
Policy-event register
Source: policy_event_table.json. 41 resource-nationalism events, 2007–2026; the lever is the NPV channel (E export, N nationalization, L local-content, T tax/royalty). Primary-source citations verified for 40 of 41 events.
Country | Year | Lever | Regime | Named instrument | Primary source
Argentina | 2012 | Nationalization | interventionist | YPF 51% expropriation (Repsol) | Ley 26.741 (2012), Soberanía Hidrocarburífera; Boletín Oficial, 7 May 2012
Argentina | 2018 | Export restriction | crisis | export duties on mining (DNU 793/2018) | Decreto 793/2018, Boletín Oficial, 4 Sep 2018
Argentina | 2018 | Tax/royalty | crisis | export-duty package | Decreto 793/2018 (mod. Decretos 865/2018, 1201/2018), Boletín Oficial, 2018
Argentina | 2019 | Tax/royalty | crisis | Solidarity Law duty hikes | Ley 27.541 (2019), Ley de Solidaridad Social; Boletín Oficial, 23 Dec 2019
Australia | 2012 | Tax/royalty | orthodox | Minerals Resource Rent Tax (MRRT) | Minerals Resource Rent Tax Act 2012 (Cth), No. 13 of 2012 (in force 1 Jul 2012)
Bolivia | 2007 | Nationalization | interventionist | ICSID withdrawal | Denunciation of the ICSID Convention; ICSID depositary notice 2 May 2007 (eff. 3 Nov 2007)
Bolivia | 2008 | Nationalization | interventionist | hydrocarbon/mining nationalizations | Decreto Supremo Nº 29541 (1 May 2008), Gaceta Oficial de Bolivia
Bolivia | 2012 | Nationalization | interventionist | BIT abrogation; sector state control | Termination of U.S.–Bolivia BIT (eff. 10 Jun 2012); Decreto Supremo Nº 1214 (1 May 2012)
Bolivia | 2017 | Local content | interventionist | YLB lithium state monopoly | Ley Nº 928 (27 Apr 2017), Ley de la Empresa YLB; Gaceta Oficial de Bolivia
Chile | 2010 | Tax/royalty | orthodox | royalty increase (post-earthquake reconstruction) | Ley 20.469 (2010), tributación de la actividad minera; Diario Oficial, 21 Oct 2010
Chile | 2023 | Nationalization | interventionist | National Lithium Strategy: state control (Codelco/SQM) | Estrategia Nacional del Litio (Gobierno de Chile, 20 Apr 2023) — policy announcement, not a statute
Chile | 2023 | Tax/royalty | interventionist | mining royalty law | Ley Nº 21.591, Royalty a la Minería; Diario Oficial, 10 Aug 2023 (eff. 1 Jan 2024)
Chile | 2023 | Local content | interventionist | domestic value-add via state JV | Estrategia Nacional del Litio (Gobierno de Chile, 20 Apr 2023) — policy announcement, not a statute
DRC | 2025 | Export restriction | crisis | cobalt export suspension | Décision Nº 001/ARECOMS/2025 (22 Feb 2025), Democratic Republic of the Congo
Ghana | 2023 | Export restriction | orthodox | Green Minerals Policy raw-lithium ban | Green Minerals Policy (Ghana Cabinet, 8 Aug 2023) — policy, not a statutory instrument
Ghana | 2023 | Local content | orthodox | local-processing mandate | Green Minerals Policy (Ghana Cabinet, 8 Aug 2023) — policy, not a statutory instrument
Guinea | 2025 | Nationalization | crisis | mining-licence revocations | Presidential decree revoking mining permits (Transitional Presidency), 14 May 2025
Indonesia | 2009 | Local content | interventionist | Law 4/2009 domestic-processing requirement | Law No. 4 of 2009 on Mineral and Coal Mining (Indonesia), Arts. 102–104, 170
Indonesia | 2014 | Export restriction | interventionist | nickel ore export ban (partial) | Government Regulation (PP) No. 1 of 2014 and MEMR Regulation No. 1 of 2014 (11 Jan 2014)
Indonesia | 2020 | Export restriction | interventionist | nickel ore export ban (full) | MEMR Regulation No. 11 of 2019 (nickel export ban advanced to 1 Jan 2020)
Indonesia | 2023 | Export restriction | interventionist | bauxite export ban | Executive action under Law No. 3 of 2020 and GR No. 96 of 2021; effective 10 Jun 2023
Mali | 2023 | Tax/royalty | crisis | new mining code; state stakes | Loi n°2023-040 du 29 août 2023, Code minier; Journal Officiel de la République du Mali
Mali | 2024 | Nationalization | crisis | Barrick/Resolute detentions; asset seizure | De facto seizure/detentions, Nov 2024–Jan 2025 (Barrick press release, 27 Nov 2024) — enforcement action, not a decree
Mexico | 2022 | Nationalization | interventionist | lithium declared national property (LitioMex) | Reforma a la Ley Minera, DOF 20 Apr 2022; Decreto que crea LitioMx, DOF 23 Aug 2022
Mexico | 2023 | Nationalization | interventionist | LitioMex concession revocations | Decreto de Zona de Reserva Minera de litio (Sonora), DOF 18 Feb 2023; concession cancellations, Sec. de Economía
Namibia | 2023 | Export restriction | orthodox | unprocessed critical-minerals export ban | Cabinet directive / Ministry of Mines and Energy, 8 Jun 2023 (unprocessed critical-minerals export ban)
Namibia | 2023 | Local content | orthodox | domestic-refining requirement | Cabinet directive, 8 Jun 2023 (local value-addition requirement)
Niger | 2024 | Nationalization | crisis | Orano uranium permit revocation | Government of Niger decree withdrawing Orano's Imouraren permit, 19–20 Jun 2024
Nigeria | 2022 | Export restriction | interventionist | raw-ore export ban | Ministry of Mines and Steel Development policy pronouncement, Jul 2022
Nigeria | 2022 | Local content | interventionist | local-processing push | Ministry of Mines and Steel Development policy pronouncement, Jul 2022
Peru | 2011 | Tax/royalty | orthodox | gravamen especial a la mineria | Ley Nº 29790, Gravamen Especial a la Minería; El Peruano, 28 Sep 2011
Venezuela | 2011 | Nationalization | crisis | gold-sector nationalization | Decreto-Ley Nº 8.413 (2011); Gaceta Oficial Nº 39.759, 16 Sep 2011
Zambia | 2008 | Tax/royalty | interventionist | windfall tax | Mines and Minerals Development Act No. 7 of 2008 (Zambia); windfall tax, eff. 1 Apr 2008
Zambia | 2019 | Nationalization | interventionist | KCM/Vedanta forced liquidation | KCM provisional liquidation, High Court of Zambia (Lusaka), May 2019 (ZCCM-IH petition) — court order, not a statute
Zambia | 2019 | Tax/royalty | interventionist | mineral royalty increase | Mines and Minerals Development (Amendment) Act No. 18 of 2018 (Zambia), eff. 1 Jan 2019
Zimbabwe | 2022 | Export restriction | interventionist | SI 213/2022 raw-lithium export ban | Statutory Instrument 213 of 2022 (Zimbabwe)
Zimbabwe | 2022 | Local content | interventionist | beneficiation mandate | Statutory Instrument 213 of 2022 (Zimbabwe) — beneficiation facet of the same order
Zimbabwe | 2023 | Export restriction | interventionist | SI 5/2023 base-minerals extension | Statutory Instrument 5 of 2023 (Zimbabwe); amended by SI 57 of 2023
Zimbabwe | 2025 | Tax/royalty | interventionist | 10% lithium-concentrate export tax | [CHECK — export-tax rate and enacting instrument unverified]
Zimbabwe | 2025 | Local content | interventionist | concentrate export ban announced (2027) | Ministry of Mines and Mining Development announcement, 11 Jun 2025 (concentrate export ban from 1 Jan 2027)
Zimbabwe | 2026 | Export restriction | interventionist | raw-mineral/concentrate export suspension | Ministry of Mines and Mining Development directive, 25 Feb 2026 (raw-mineral/concentrate export suspension)
One cell remains [CHECK] (Zimbabwe 2025 concentrate tax — rate/instrument unverified). Four instruments activate two levers at once; see Robustness tab.

## Driver attribution
Driver attribution (lithium)
Source: table5_regen.json. Sobol top-variance driver vs the factor that decided the realized outcome; the cost audit resolves the one case the variance ranking misses (Table 5).
Project | Sobol top driver | Realized decisive factor | Match | Cost-audit percentile | Outcome
Olaroz S1 | price | price | yes | 20th pct | producing, profitable in boom
Mt Cattlin | price | price | yes | 23th pct | shut 2013 on price, restart 2016
Mt Marion | price | price | yes | 22th pct | producing through boom
Pilgangoora | price | price | yes | 21th pct | survived trough, boom winner
Altura Pilgangoora | price | price | yes | 21th pct | receivership 2020 (price+debt), equity wiped
Nemaska Whabouchi | capital | capital | yes | 22th pct | C$375M shortfall revealed 2019; CCAA, ~55% spent, ze
Bald Hill | price | price | yes | 22th pct | administration 2019 on price
Wodgina concentrator | price | price | yes | 22th pct | mothballed 2019 on price; 60% JV sale to ALB monetiz
Cauchari-Olaroz | capital | price | no | 17th pct | producing 2023 into the price collapse
AMG Mibra | price | price | yes | 21th pct | on budget, byproduct economics, steady

## Robustness
Robustness
Sources: rf_data.json (grids) and robustness_shared_instrument.py / robustness_heldout.py (shared-instrument check).
Spearman ρ across discount × risk-aversion grid (copper)
Discount \ λ | 0.3 | 0.5 | 0.7
8% | 0.8 | 0.71 | 0.7
9% | 0.75 | 0.67 | 0.69
10% | 0.66 | 0.65 | 0.57
Copper decision-loss: % of always-enter→oracle gap closed (8% discount, λ=0.5)
Staged exp. \ χ | χ=0.25 | χ=0.50 | χ=0.75 | χ=1.00
0.1 | 94 | 87 | 81 | 75
0.3 | 93 | 87 | 81 | 76
0.5 | 93 | 87 | 81 | 76
Lithium decision loss (US$M)
workflow | 721
always enter | 1476
always walk | 1074
random | 1242
Shared-instrument sensitivity (collapse 4 two-lever instruments → 1 event each)
Quantity | Effect of collapse
Export (E) & nationalization (N) hazards | unchanged
Local-content (L) events | 8 → 4 (hazard ↓ ~30%)
Price-boom multiplier (β) | 2.6× → 2.1×
Held-out prediction test | 3/4 beats base, PASS (both panels; +0.29 vs +0.31 nats)